## Sheet1
Sprint Name | Module name | Page Name |  | Efforts (working days) |  | Start date | End date
Sprint 1 | Dashboard (one graph for - order, company, products)
| Log in |  |  | 3 |  | 2014-07-10 | 2014-07-14
login page
forgot password
locked screen
| Product mgmt |  |  | 5 |  | 2014-07-15 | 2014-07-21
Listing page (including pagination + search)
| Company mgmt |  |  | 5 |  | 2014-07-22 | 2014-07-28
Listing page (including pagination + search)
Demo for the sprint
Sprint 2 | User mgmt |  |  | 5 |  | 2104-07-29 | 2014-08-04
Listing page (including pagination + search)
details page (user activities + user details)
Sorting (admin, client, staff)
Create user
Activities (all users)
| Order Mgmt |  |  | 4 |  | 2014-08-05 | 2014-08-08
order listing
create order
Demo for the sprint
Sprint 3 | Tracking |  |  | 4 |  | 2014-08-11 | 2014-08-14
Job grid (for internal/ external)
upload files (internal)
timeline (for internal user)
| Scheduler |  |  | 4 |  | 2014-08-18 | 2014-08-21
|  | left panel (sorting as per the jobs and users) | 1
|  | assumption (deleting the jobs assigned do the staff) | 2
|  | creation of event | 1
Demo for the sprint
| Buffer (RnD, bugs solving as per sprints, sprint demo) |  |  | 5 |  | 2014-08-22 | 2014-08-28
| Testing (UAT & bugs solving) |  |  | 5 |  | 2014-08-29 | 2014-09-04
|  |  | Total | 40 | working days
| UI Design - will be carried out parallely. |  |  | 15 | working days